## Release_Summary
Agentic Hub Planner + Supervisor — Production Release Plan
Field | Value |  | Size | Meaning
Committed delivery model | Release 1 (14–16 weeks), Release 2 (+6 weeks), Release 3 (+6 weeks) |  | XS | 2–3 days
Committed total | 26–28 weeks |  | S | 4–5 days
Primary ownership | Planner + Supervisor layer, plus minimal orchestrator handshake and platform hooks |  | M | 1–1.5 weeks
Release 1 focus | Production core: contracts, planning, validation, supervision, telemetry, deployment baseline |  | L | 2 weeks
Release 2 focus | Trust hardening: policy-aware planning, approval awareness, replay/debugging, auditability |  | XL | 3+ weeks / cross-cutting work
Release 3 focus | Reflection / feedback hooks: trajectory artifacts, reflection payloads, feedback linkage
Roadmap Release 4 | Adaptive optimization (offline and governed)
Roadmap Release 5 | Platformization, multi-tenant maturity, broader onboarding
Release | Name | Core Build | Buffer | Total | Status
R1 | Production Core | 12–13 weeks | 2–3 weeks | 14–16 weeks | Committed
R2 | Trust Hardening | 5 weeks | 1 week | +6 weeks | Committed
R3 | Reflection / Feedback Hooks | 5 weeks | 1 week | +6 weeks | Committed
R4 | Adaptive Optimization | 6–9 weeks | 2–3 weeks | 8–12 weeks | Roadmap
R5 | Platformization | 8–10 weeks | 2–4 weeks | 10–14 weeks | Roadmap

## Release_1_Backlog
R1 — Release 1 Backlog
Timeline | 14–16 weeks
Release goal | Production Core
Epic | Feature | Type | Story / Task | Acceptance / Output | Dependency | Owner | Size | Build Weeks | Buffer | Total
Foundation | Layer C boundary | HLD | Freeze Planner / Supervisor / Orchestrator boundaries and lifecycle | Approved architecture note and sequence flow | None | Architecture | S | 0.5 | 0 | 0.5
Foundation | Contracts | LLD | Define RequestEnvelope, ExecutionPlan, TaskNode, StateCheckpoint, SupervisorDecision, ReplanRequest | Versioned Pydantic models and JSON schema exports | Layer C boundary | Engineering | M | 1 | 0.5 | 1.5
Planner | Prompt & I/O design | LLD | Design planner input/output rules, plan versioning, prompt templates, and plan metadata | Planner LLD package and prompt files | Contracts | Architecture | S | 0.5 | 0 | 0.5
Planner | Deterministic planner | Build | Implement deterministic planner for benchmark flows and template-driven intents | Working deterministic planner module | Planner prompt & I/O design | Engineering | M | 1 | 0 | 1
Planner | LLM planner | Build | Implement structured-output planner backend through provider adapter | Planner emits schema-constrained ExecutionPlan objects | Deterministic planner | Engineering | L | 2 | 0.5 | 2.5
Planner | Plan validator | Build | Implement DAG validation, normalization, and plan version manager | Validator catches cycles, missing fields, and dependency issues | LLM planner | Engineering | M | 1 | 0.5 | 1.5
Planner | Replan entry point | Build | Implement replan flow using partial state and failure reason | Replan API returns versioned replacement plan | Plan validator | Engineering | M | 1 | 0 | 1
Supervisor | Decision policy | LLD | Design thresholds, decision enums, escalation payloads, and config model | Supervisor LLD and config package | Contracts | Architecture | S | 0.5 | 0 | 0.5
Supervisor | State reader | Build | Implement state reader over real execution checkpoints | Supervisor consumes StateCheckpoint and execution events | Decision policy | Engineering | M | 1 | 0 | 1
Supervisor | Decision engine | Build | Implement continue / re-plan / escalate / stop logic | Supervisor emits governed decisions from execution state | State reader | Engineering | L | 2 | 0.5 | 2.5
Supervisor | Conflict / failure detector | Build | Add low-confidence, repeated-failure, and conflict detection | Conflict/failure triggers connected to decision engine | Decision engine | Engineering | M | 1 | 0 | 1
Integration | Orchestrator handshake | Build | Implement minimal runtime adapter for task transitions and supervisor checkpoints | Planner and Supervisor integrated into execution loop | Planner + Supervisor core | Engineering | L | 2 | 0.5 | 2.5
Observability | Trace model | Build | Instrument plan events, state transitions, validation failures, and decisions | OpenTelemetry spans and structured logs available | Orchestrator handshake | Platform | M | 1 | 0 | 1
Quality | Release tests | QA | Create golden workflows, negative-path tests, and integration suite | Release 1 test pack passes | Trace model | Engineering | M | 1 | 0.5 | 1.5
Deployment | Dev/test baseline | DevOps | Containerize services and deploy to dev/test runtime | Docker image and Azure Container Apps baseline | Release tests | Platform | M | 1 | 0.5 | 1.5

## Release_2_Backlog
R2 — Release 2 Backlog
Timeline | +6 weeks
Release goal | Trust Hardening
Epic | Feature | Type | Story / Task | Acceptance / Output | Dependency | Owner | Size | Build Weeks | Buffer | Total
Planning hardening | Policy-aware planning | Build | Inject policy metadata and role-aware constraints into planning | Plans carry policy-aware node metadata | R1 complete | Engineering | L | 2 | 0.5 | 2.5
Planning hardening | Approval nodes | Build | Insert approval checkpoints for selected high-risk flows | Approval-aware plan templates available | Policy-aware planning | Engineering | M | 1 | 0 | 1
Supervisor hardening | Risk-tier escalation | Build | Implement risk-tiered escalation matrix and unsafe-path detection | Supervisor blocks/escalates unsafe flows by configuration | R1 complete | Engineering | L | 2 | 0.5 | 2.5
Supervisor hardening | Decision explainability | Build | Attach structured reason codes and confidence bands to decisions | Decision payloads are audit-friendly | Risk-tier escalation | Engineering | S | 0.5 | 0 | 0.5
Observability | Replay bundle | Build | Generate replay/debug bundle for failed or escalated runs | Replay artifacts capture plan version, state, and config lineage | R1 traces | Platform | M | 1 | 0 | 1
Operations | Runbooks | HLD/LLD | Create Layer C incident runbook, support path, and operational checklist | Runbook and support guide approved | Replay bundle | Architecture | S | 0.5 | 0 | 0.5
Governance | Version control rules | LLD | Version prompts, templates, thresholds, and policy config | Release change-control rules documented | R1 complete | Architecture | S | 0.5 | 0 | 0.5
Quality | Trust hardening tests | QA | Add governance-path, escalation-path, and replay tests | Release 2 suite passes | All R2 build items | Engineering | M | 1 | 0.5 | 1.5

## Release_3_Backlog
R3 — Release 3 Backlog
Timeline | +6 weeks
Release goal | Reflection / Feedback Hooks
Epic | Feature | Type | Story / Task | Acceptance / Output | Dependency | Owner | Size | Build Weeks | Buffer | Total
Planner reflection | Critique payloads | Build | Emit planner critique artifacts and alternate-plan support fields | Plan critique payload schema and outputs available | R2 complete | Engineering | M | 1 | 0 | 1
Supervisor reflection | Reflection triggers | Build | Add reflection-trigger policy and structured evaluation payloads | Supervisor emits reflection/evaluation-ready signals | R2 complete | Engineering | M | 1 | 0 | 1
Trajectory | Lineage enrichment | Build | Enrich traces with plan revisions, failed nodes, decision lineage, and intervention reasons | Trajectory artifacts ready for review workflows | R1 traces | Platform | L | 2 | 0.5 | 2.5
Feedback | Feedback schema | LLD | Define feedback event schema and trace-linking keys | Feedback contract and linkage keys published | R2 complete | Architecture | S | 0.5 | 0 | 0.5
Feedback | Feedback capture hooks | Build | Add user/system review hooks linked to plan and decision lineage | Feedback events captured against run lineage | Feedback schema | Engineering | M | 1 | 0 | 1
Evaluation | Plan/decision dashboards | Build | Create dashboard views for plan quality, intervention quality, and repeat failures | Release 3 dashboards available | Lineage enrichment | Platform | M | 1 | 0 | 1
Integration | Reflection service hooks | Build | Publish reflection-ready payloads for downstream reflection services or evaluation jobs | Offline-ready artifact export path available | Planner & Supervisor reflection | Engineering | M | 1 | 0.5 | 1.5
Quality | Release 3 validation | QA | Validate artifact completeness, linkage, and feedback capture | Release 3 suite passes | All R3 build items | Engineering | M | 1 | 0.5 | 1.5

## Roadmap_Releases
R4/R5 — Roadmap Releases
Timeline | Roadmap
Release goal | Later releases beyond the committed 26–28 week window
Epic | Feature | Type | Story / Task | Acceptance / Output | Dependency | Owner | Size | Build Weeks | Buffer | Total
Adaptive Optimization | Offline policy tuning | Roadmap | Add offline routing and policy optimization workflows | Shadow-mode candidate policies and promotion process | After R3 | Shared | XL
Adaptive Optimization | Learning lab integration | Roadmap | Connect Reflection/Feedback artifacts to governed offline optimization lab | Offline-ready pipeline integration | After R3 | Shared | L
Platformization | Multi-tenant hardening | Roadmap | Add multi-tenant controls and broader onboarding model | Reusable platform service maturity | After R4 | Shared | XL
Platformization | SLA / FinOps | Roadmap | Operationalize SLA/SLO and cost controls for the shared service | Platformized operating model | After R4 | Shared | L

## Timeline
Planner + Supervisor Release Timeline (26–28 weeks committed)
Release | Workstream | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
R1 | Foundation + contracts | 1 | 2
R1 | Planner build | 3 | 8
R1 | Supervisor build | 7 | 10
R1 | Integration + telemetry | 9 | 13
R1 | Release test + deploy | 13 | 16
R2 | Policy/approval planning | 17 | 19
R2 | Supervisor trust hardening | 17 | 20
R2 | Replay/runbooks/tests | 20 | 22
R3 | Reflection payloads | 23 | 25
R3 | Trajectory/feedback hooks | 23 | 26
R3 | Dashboards + validation | 26 | 28